## Instructions
Work Breakdown Structure (WBS) Gantt Chart
A Gantt Chart reflects the project schedule, which is composed of the WBS, the projected dates each task is to be started and completed, the milestones, and the resources assigned.
A milestone is a significant event in your project and will act as primary checkpoints for the project’s progress and budget control. These are generally at delivery of a highly visible or significant product or result (e.g., equipment delivery, final test results, final review report, implementation of a reform initiative, review meeting, approval checkpoint). Not every task completion date in the project will be a milestone, but every milestone should be tied to a deliverable.
Milestones are targets that should be met without deviation from the original project duration estimate. If they are not met, it is likely that the project will not finish on time. Milestones may be listed in a separate table however they must be clearly identified in the WBS.
All the tasks may not be known at the start of the project; you may need to break the major tasks down further. The development of a WBS relies on the progressive breaking down of the project into units of work. Through the process of progressively dividing an activity of work into something more manageable you will finally arrive at discrete work tasks which you will be able to estimate, assign, cost, plan and control.
The main objective of the WBS is to identify and list all of the work tasks which are needed to complete the project.
Critical WBS Dependencies
It is essential that the dependencies between related tasks and subtasks be understood to ensure that tasks are sequenced correctly and that the critical path of a project is recognised.
Using the WBS determine the relationship between work performed in a given task or subtask with the work performed in other tasks or subtasks. Identify the predecessor and successor activities, the nature of the dependency between them and the amount of gap, lag time or overlap that can occur between the activities. Indicate whether each dependency is Start to Start, Finish to Finish, Start to Finish or Finish to Start.
Identify any tasks within a related project on which this project is dependent and describe the relationship. Account for these dependencies in the project dependencies and include critical dependencies in the risk analysis.
Guidelines for WBS tasks
· Should be measurable in terms of cost, effort, resource and time
· Result in a single end product
· Identify a clear start and end date
· Be assigned to a single project team member
Note: Most project managers “brainstorm” the WBS identification and sequencing with their key project team members. Using post-it notes and a white-board can assist the process.
Published Aug 2015. Next review 2024. © State of NSW (Agency for Clinical Innovation) CC-ND-BY

## Overall Timeline
Status
On track
Monitor
Escalate
Completed
Project Time line: enter project title
| Project phases & Activities | [5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
[7 empty] | Plan |  | Assess |  |  | Operationalise
|  |  | Month Beginning |  |  |  | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date
|  |  | Responsible | Status | Completion date | Comments
Plan
Project Management Plan
| Project Team |  | responsible for task
| Communications & Stakeholder Management Plan |  | responsible for task
| Risk Mitigation plan |  | responsible for task
Project launch
Assess
Organise workshops, interviews and attendees
Patients' stories
Review Previous initiatives
Surveys
Conduct tagalongs & observations
Map existing processes
Data collection & analysis
Identify issues
Prioritise key issues
Build case for change
Prepare diagnostic A3
Develop solutions
Test solutions
Gain feedback from staff on solutions
Develop Solution design A3
Develop implementation A3
Ensure data measures are in place to monitor change
Operationalise
To complete according to solutions
Solution 1
Solution 2
Solution 3
Solution 4
Solution 5…
Change management
Review of data measures
Analysis and report writing
Project Management Tasks
Project Team Meetings
Sponsor status updates
Steering Committee Meeting
Please note that this template only includes generic tasks linked with project management.
This document should also include project specific tasks and deliverables as soon as they are known.
It is the role of the project lead to ensure critical dependencies are identified and to monitor the project's progress.
This document should be updated regularly.

## Plan Phase
Project Time line: enter project title
Project phases & Activities | [6 empty] | Plan
|  |  | Week Beginning |  |  |  | date | date | date | date | date | date | date | date
|  |  | Responsible | Status | Completion date | Comments
Plan
Project Management Plan
Draft Project Management Plan
Meet with executive sponsor
Confirm scope and objectives
Confirm Steering Committee membership
Gain Signoff for Project Management Plan
Project Team
Confirm roles and responsibilities
Train and orient project team
Communications & Stakeholder Management Plan
Set up Steering Committee
Develop Terms of Reference
Identify & confirm key stakeholders
Circulate stakeholder list for expansion
Develop communication plan
Draft communication plan
Commence Stakeholder engagement
Prepare communications e.g status reports
Risk Mitigation plan
Identify & log risks & issues
Develop risk mitigation plan
Manage risk plan
Project launch

## Assess Phase
Project Time line: enter project title
Project phases & Activities | [6 empty] | Assess
|  |  | Week Beginning |  |  |  | date | date | date | date | date | date | date | date | date | date | date | date
|  |  | Responsible | Status | Completion date | Comments
Assess
Organise workshops, interviews and attendees
Run workshops / focus groups
Interview key stakeholders
Patients' stories
Invite patients to participate
Conduct interviews
Document stories
Analyse stories
Review Previous initiatives
Surveys
Define questions
Send out surveys
Gather and analyse information
Conduct tagalongs & observations
Map existing processes
Data collection & analysis
Identify data requirements
Obtain data
Analyse data
Identify issues
Prioritise key issues
Build case for change
Prepare diagnostic A3
Prepare draft
Circulate draft for review
Finalise
Develop solutions
Impact assessment
Solution costs & benefits
Determine accountabilities
Agree on solution prioritisation
Test solutions
Gain feedback from staff on solutions
Develop Solution design A3
Prepare draft
Circulate draft for review
Finalise
Develop implementation A3
Prepare draft
Circulate draft for review
Finalise plan
Ensure data measures are in place to monitor change

## Operationalise Phase
Project Time line: enter project title
Project phases & Activities
Operationalise
|  |  | Week Beginning |  |  |  | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date
|  |  | Responsible | Status | Completion date | Comments
Operationalise
To complete according to solutions
Solution 1
Solution 2
Solution 3
Solution 4
Solution 5…
Change management
Ongoing change management activities
Promote & develop sustainability
Gain buy in & generate ownership & enthusiasm
Develop reinforcement strategies
Review of data measures
Analysis and report writing