## Instructions
Work Breakdown Structure (WBS) Gantt Chart
A Gantt Chart reflects the project schedule, which is composed of the WBS, the projected dates each task is to be started and completed, the milestones, and the resources assigned.
A milestone is a significant event in your project and will act as primary checkpoints for the project’s progress and budget control. These are generally at delivery of a highly visible or significant product or result (e.g., equipment delivery, final test results, final review report, implementation of a reform initiative, review meeting, approval checkpoint). Not every task completion date in the project will be a milestone, but every milestone should be tied to a deliverable.
Milestones are targets that should be met without deviation from the original project duration estimate. If they are not met, it is likely that the project will not finish on time. Milestones may be listed in a separate table however they must be clearly identified in the WBS.
All the tasks may not be known at the start of the project; you may need to break the major tasks down further. The development of a WBS relies on the progressive breaking down of the project into units of work. Through the process of progressively dividing an activity of work into something more manageable you will finally arrive at discrete work tasks which you will be able to estimate, assign, cost, plan and control.
The main objective of the WBS is to identify and list all of the work tasks which are needed to complete the project.
Critical WBS Dependencies
It is essential that the dependencies between related tasks and subtasks be understood to ensure that tasks are sequenced correctly and that the critical path of a project is recognised.
Using the WBS determine the relationship between work performed in a given task or subtask with the work performed in other tasks or subtasks. Identify the predecessor and successor activities, the nature of the dependency between them and the amount of gap, lag time or overlap that can occur between the activities. Indicate whether each dependency is Start to Start, Finish to Finish, Start to Finish or Finish to Start.
Identify any tasks within a related project on which this project is dependent and describe the relationship. Account for these dependencies in the project dependencies and include critical dependencies in the risk analysis.
Guidelines for WBS tasks
· Should be measurable in terms of cost, effort, resource and time
· Result in a single end product
· Identify a clear start and end date
· Be assigned to a single project team member
Note: Most project managers “brainstorm” the WBS identification and sequencing with their key project team members. Using post-it notes and a white-board can assist the process.

## Project WBS
Status
On track
Monitor
Escalate
Completed
Project Plan: enter project title
| Project phases & Activities | [5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
[7 empty] | 1: Project initiation; 5: Diagnostic; 11: Solution Design; 16: Imp-Planning; 19: Implementation | [11 empty] | Evaluation
|  |  | Week Beginning |  |  |  | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date
|  |  | Responsible | Status | Completion date | Comments
Assess pre-project readiness
Prepare project application
Attendance at Centre for HealthCare Redesign CHR
Plan & Mobilise Project
Project Management plan
|  | Draft Project Management Plan | responsible for task
|  | Meet with executive sponsor | responsible for task
|  | Confirm scope and objectives | responsible for task
| Project Team |  | responsible for task
|  | Confirm roles and responsibilities | responsible for task
|  | Train and orient project team | responsible for task
| Communications & Stakeholder Management Plan |  | responsible for task
|  | Set up Steering committee | responsible for task
|  | Identify committee members | responsible for task
|  | Develop Terms of Reference | responsible for task
|  | Identify & confirm key stakeholders | responsible for task
|  | Circulate stakeholder list for expansion | responsible for task
|  | Stakeholder engagement | responsible for task
|  | Develop communication plan | responsible for task
|  | Draft communication plan | responsible for task
|  | Prepare communications e.g status reports | responsible for task
| Risk Mitigation plan |  | responsible for task
|  | Identify & log risks & issues | responsible for task
|  | Develop risk mitigation plan | responsible for task
|  | Manage risk plan | responsible for task
| Prepare initiation presentation |  | responsible for task
Project launch
Diagnostic Phase
| Organise workshops, interviews and attendees |  | audit against 7 key principles |  | staff knowledge and attitude
| Patients' stories |  | environmental audit |  | interviews with staff
|  | Invite patients to participate | medical file audit |  | #movements/referrals Caseplan
|  | Conduct interviews | staff knowledge and attitude survey |  | interviews with patients and carers
|  | Write and validate stories | #movements/referrals Caseplan |  | interviews with staff and survey re impprovement of key principles
|  | Analyse stories | interviews with patients and carers |  | interview with staff. Carers and patients re: value of cHOPs
| Review Previous initiatives |  | # training sessions |  | # receiving cognitive screening<24 hours/# patients
| Surveys |  | # staff attending training sessions |  | # having delirum risk assessed/#patients
|  | Define questions | interviews to identify success factors |  | # ward moves
|  | Send out surveys | changes to physical environment plan developed; % of plan activities completed |  | # restraints
|  | Gather and analyse information | # patients identified with or at risk of delirium |  | # case plans developed/#patients
| Map existing processes |  | Survey of awareness of CHOPs |  | # case plans implementated/#patients
| Identify issues |  | survey of carer experience |  | LOS
| Root Cause Analysis |  | # referrals made |  | Readmissions
| Data collection & analysis |  | # patient journey system |  | complications
|  | Identify data requirements | # of patients with "know your patient" system |  | functional status
|  | Obtain data | # patients coded
|  | Analyse data | # patients correctly coded
Confirm hypothesis
Prioritise key issues
Review best practice
Build case for change
Prepare diagnostic report
Prepare draft report
Circulate draft for review
Finalise report
Prepare diagnostic presentation
Solution Design
| Organise workshop/ focus group & attendees |  | System/Staff/Carers |  | Strategies to address 7 principles
|  | Run workshop & focus groups | options
| Identify implementation team |  | pathways
| Develop solutions |  | referral points
|  | Impact assessment | transfer of care
|  | Solution costs & benefits | tools available
|  | Determine accountabilities | training program developed
|  | Determine ouctome benchmarks & KPIs | training options
|  | Agree on solution prioritisation | HETI online modules delirum and demntia
| Test solutions |  | forum
| Develop Solution design report |  | know your patient system (in place and accessible)
Prepare draft report
Circulate draft for review
Finalise solution design report
Implementation Planning
Gain feedback from staff on solutions
Develop implementation plan
Prepare draft plan
Circulate draft for review
Finalise implementation team
Finalise plan
Prepare implementation presentation
Implementation
To complete according to solutions
Solution 1
Task 1
Task 2
Task 3
Solution 2
Task 1
Task 2
Task 3
Solution 3
Solution 4
Solution 5…
Change management
Ongoing change management activities
Promote & develop sustainability
Gain buy in & generate ownership & enthusiasm
Develop reinforcement strategies
Evaluation
Project Management Tasks |  |  | # training sessions |  | staff knowledge and attitude | LOS
| Project Team Meetings |  | # staff attending training sessions |  | interviews with staff | Readmissions
| Sponsor status updates |  | interviews to identify success factors |  | #movements/referrals Caseplan | complications
| Steering Committee Meeting |  | changes to physical environment plan developed; % of plan activities completed |  | interviews with patients and carers | functional status
|  |  | # patients identified with or at risk of delirium |  | interviews with staff and survey re impprovement of key principles
|  |  | Survey of awareness of CHOPs |  | interview with staff. Carers and patients re: value of cHOPs
|  |  | survey of carer experience |  | # receiving cognitive screening<24 hours/# patients
|  |  | # referrals made |  | # having delirum risk assessed/#patients
|  |  | # patient journey system |  | # ward moves
|  |  | # of patients with "know your patient" system |  | # restraints
|  |  | # patients coded |  | # case plans developed/#patients
|  |  | # patients correctly coded |  | # case plans implementated/#patients
KEY (feel free to make your own keys to populate the project plan, the ones below are just examples)
Deliverable / Milestone
Project Team Meeting
Steering Committee Meeting
Sponsor status update
Critical WBS Dependencies
Training- CHR
Phase duration
Activity Duration
Published Oct 2015. Next review 2025. © State of NSW (Agency for Clinical Innovation) CC-ND-BY