## Instructions
Work Breakdown Structure (WBS) Gantt Chart
A Gantt Chart reflects the project schedule, which is composed of the WBS, the projected dates each task is to be started and completed, the milestones, and the resources assigned.
A milestone is a significant event in your project and will act as primary checkpoints for the project’s progress and budget control. These are generally at delivery of a highly visible or significant product or result (e.g., equipment delivery, final test results, final review report, implementation of a reform initiative, review meeting, approval checkpoint). Not every task completion date in the project will be a milestone, but every milestone should be tied to a deliverable.
Milestones are targets that should be met without deviation from the original project duration estimate. If they are not met, it is likely that the project will not finish on time. Milestones may be listed in a separate table however they must be clearly identified in the WBS.
All the tasks may not be known at the start of the project; you may need to break the major tasks down further. The development of a WBS relies on the progressive breaking down of the project into units of work. Through the process of progressively dividing an activity of work into something more manageable you will finally arrive at discrete work tasks which you will be able to estimate, assign, cost, plan and control.
The main objective of the WBS is to identify and list all of the work tasks which are needed to complete the project.
Critical WBS Dependencies
It is essential that the dependencies between related tasks and subtasks be understood to ensure that tasks are sequenced correctly and that the critical path of a project is recognised.
Using the WBS determine the relationship between work performed in a given task or subtask with the work performed in other tasks or subtasks. Identify the predecessor and successor activities, the nature of the dependency between them and the amount of gap, lag time or overlap that can occur between the activities. Indicate whether each dependency is Start to Start, Finish to Finish, Start to Finish or Finish to Start.
Identify any tasks within a related project on which this project is dependent and describe the relationship. Account for these dependencies in the project dependencies and include critical dependencies in the risk analysis.
Guidelines for WBS tasks
· Should be measurable in terms of cost, effort, resource and time
· Result in a single end product
· Identify a clear start and end date
· Be assigned to a single project team member
Note: Most project managers “brainstorm” the WBS identification and sequencing with their key project team members. Using post-it notes and a white-board can assist the process.
SHPN (ACI) 210210

## Overall Timeline
Status
On track
Monitor
Escalate
Completed
Project Time line: My rehab, my journey - Gadjigadji
| Project phases & Activities | [5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
[7 empty] | Plan |  | Assess |  |  | Operationalise | [12 empty] | Evaluate
|  |  | Month Beginning |  |  |  | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date | date
|  |  | Responsible | Status | Completion date | Comments
Plan
Establish small multidisciplinary team
Appoint sponsor
Appoint cultural collaborator/ward champion
Meet with ALO/Social work department
Appoint a steering /governance committee
Prepare a communication plan
Establish timelines, roles and responsibilities
Discuss an evaluation approach
Assess
Conduct an assessment of the service using service audit tool
Identify priority areas for action
Establish project plan and timeline
Communicate the project
Operationalise
Review action items
Review progress against the plan
Monitor using service audit tool
Evaluate
Utilise patient and visitor cultural safety survey
Repeat service audit tool
Communicate the change
Repeat the cycle
Project Management Tasks
Project Team Meetings
Sponsor status updates
Steering Committee Meeting