## Sheet1
Phase | Key Milestone | Time to complete | Month to commence | Month
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Pre-Impl. | Site endorsed by ECI to implement NDEC | - | 2016-07-01
Pre-Impl. | Local Implementation Team established | 1 month | 2016-07-01 | bar: Month 1
Pre-Impl. | Project Plan developed and endorsed locally | 1 month | 2016-08-01 | bar: Month 2
Pre-Impl. | Communications Plan developed | 1 month | 2016-08-01 | bar: Month 2
Pre-Impl. | Pre-implementation Clinical Practice audits | 2 months | 2016-09-01 | bar: Month 3 to Month 4
Pre-Impl. | Pre-implementation Patient and Staff surveys | 2 months | 2016-09-01 | bar: Month 3 to Month 4
Pre-Impl. | RN Skills Mapping & Self-assessment | 1 month | 2016-09-01 | bar: Month 3
Pre-Impl. | Patient Care Documents* endorsed locally | 6 months | 2016-09-01 | bar: Month 3 to Month 8
Impl. | RN Prerequisites and mandatory training | 3 months | 2016-11-01 | bar: Month 5 to Month 7
Impl. | RNs complete NDEC e-Learning modules | 3 months | 2017-01-01 | bar: Month 7 to Month 9
Impl. | Face to face education completed | 3 months | 2017-01-01 | bar: Month 7 to Month 9
Impl. | RNs' competency assessed satisfactorily | 3 months | 2017-01-01 | bar: Month 7 to Month 9
Impl. | Clinical Information Systems determined | 4 months | 2017-02-01 | bar: Month 8 to Month 11
Impl. | Clinical resources in place | 2 months | 2017-05-01 | bar: Month 11 to Month 12
Impl. | NDEC "Live" | Ongoing | 2017-07-01 | bar: Month 13 to Month 24
Post-Impl. | Post-implementation Clinical Practice audits | Ongoing | 2017-08-01 | bar: Month 14 to Month 24
Post-Impl. | Post-implementation Patient and Staff surveys | Ongoing | 2017-08-01 | bar: Month 14 to Month 24
Post-Impl. | RN refresher / recredentialing (annual) | 3 Months | 2018-04-01 | bar: Month 22 to Month 24
* | Nurse Management Guidelines
Medication Standing Orders
Patient Discharge Factsheets
Discharge Checklist
Formulas:
Month to commence = EDATE([Month to commence, row above],0)
Note on Q2: Nick Goryl: "Go live" date should be 12 months from commencement. Additional support/advice can be sought from the ECI if this can't be achieved.
Note on W2: Nick Goryl: If after additional support / advice has been provided, NDEC is not live within 18 months of commencement, the ECI may consider withdrawing support for implementation at site.
Note on D3: Nick Goryl: Insert the month your site was endorsed and the rest of this column will populate automatically, giving you a plan as to when work on each milestone needs to commence.